## SPRINT BACKLOG
SPRINT [NUMBER] BACKLOG
ID | User Story | Tasks | Owner | Status | Estimated effort | Day 1 16-Mar | Day 2 17-Mar | Day 3 18-Mar | Day 4 19-Mar | Day 5 20-Mar | Day 6 23-Mar | Day 7 24-Mar | Day 8 25-Mar | Day 9 26-Mar | Day 10 27-Mar | Day 11 30-Mar | Day 12 31-Mar | Day 13 1-Apr | Day 14 2-Apr | Day 15 3-Apr
US001 | As a user I need to be able to register and log in to my account with a user-id and password | Design and build login/registration UI with form validation |  | Not Started | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement backend authentication, session handling and dashboard redirect |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US002 | As a logged-in user I need to manage my profile so that my account details are kept up to date | Build profile management page with editable fields |  | Not Started | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement save functionality with confirmation message on success |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US003 | As a user I need to upload documents in PDF, PNG, or JPG format so that the system can process them | Build document upload UI with file-type validation (PDF, PNG, JPG) |  | Not Started | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement backend upload handler and file storage pipeline |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US004 | As a user I need the system to run OCR on image-based uploads so that raw text is extracted automatically | Integrate Tesseract OCR engine for image-based document uploads |  | Not Started | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test OCR output and handle edge cases (low-res, skewed images) |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US005 | As a user I need the system to parse and clean extracted text and auto-detect the document type | Implement text cleaning pipeline (strip headers, footers, page numbers) |  | Not Started | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Build document type classifier (Contract, NDA, T&Cs, Privacy Policy) |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US006 | As a user I need extracted text and metadata to be stored in the database linked to my account | Design DB schema and implement storage layer for documents and metadata |  | Not Started | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Link stored documents to authenticated user accounts |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US007 | As a user I need to view a history of all uploaded documents with their date, type, and status | Build document history page listing uploads with date, type, and status |  | Not Started | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Add sorting and filtering to history view (by date, type, status) |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US008 | As a user I need to re-open, re-analyze, or delete past documents from my document history | Implement re-open and re-analyze actions on history documents |  | Not Started | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement delete functionality with confirmation prompt |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PROJECT DETAILS
PROJECT NUMBER | PROJ-001
PROJECT NAME | Legal Document Clause Analyzer
PROJECT MANAGER | Ayush, Rishab
DATE | 16 March 2025
VERSION | 1.0

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Deployment Plan Template
Product Backlog Template
Project Management Templates