## PRODUCT BACKLOG
PRODUCT BACKLOG
User Story ID | User Story | Estimate (size) | Priority | Sprint | Task owner | Estimated effort
US001 | As a user I need to be able to register and log in to my account with a user-id and password | Small | 1 | 1 |  | 8
US002 | As a logged-in user I need to manage my profile so that my account details are kept up to date | Small | 2 | 1 |  | 8
US003 | As a user I need to upload documents in PDF, PNG, or JPG format so that the system can process them | Medium | 1 | 1 |  | 24
US004 | As a user I need the system to run OCR on image-based uploads so that raw text is extracted automatically | Medium | 1 | 1 |  | 24
US005 | As a user I need the system to parse and clean extracted text and auto-detect the document type (Contract, NDA, etc.) | Medium | 2 | 1 |  | 24
US006 | As a user I need extracted text and document metadata to be stored in the database linked to my account | Small | 2 | 1 |  | 8
US007 | As a user I need to view a history of all previously uploaded documents with their date, type, and processing status | Small | 3 | 1 |  | 8
US008 | As a user I need to be able to re-open, re-analyze, or delete past documents from my document history | Small | 3 | 1 |  | 8
US009 | As a user I need the system to generate a concise plain-English summary of an uploaded legal document | Large | 1 | 2 |  | 40
US010 | As a user I need the summary to be structured into sections (Purpose, Parties, Obligations, Duration, Termination) | Medium | 2 | 2 |  | 24
US011 | As a user I need to choose between a short summary (3-5 sentences) and a detailed section-by-section breakdown | Small | 3 | 2 |  | 8
US012 | As a user I need the system to extract key clauses from my document and display them in a readable format | Large | 1 | 2 |  | 40
US013 | As a user I need the system to flag potentially high-risk or unfavorable clauses with a risk level (Low, Medium, High) | Large | 1 | 2 |  | 40
US014 | As a user I need to see a Risk Summary card at the top of the analysis page highlighting all detected risk flags | Medium | 2 | 2 |  | 16
US015 | As a legal professional I need to add manual annotations and override AI-generated risk flags on clauses | Medium | 3 | 2 |  | 16
US016 | As a user I need to view and export the document summary and clause analysis from the document page | Small | 3 | 2 |  | 8
US017 | As a user I need an interactive chat interface on each document's analysis page so I can ask questions about the document | Medium | 1 | 3 |  | 24
US018 | As a user I need the Q&A system to use a RAG pipeline to retrieve relevant document passages and generate accurate answers | Large | 1 | 3 |  | 40
US019 | As a user I need each answer to display the source snippet from the document for transparency | Small | 2 | 3 |  | 8
US020 | As a user I need the chat to maintain conversation history within the session so I can ask follow-up questions | Small | 2 | 3 |  | 8
US021 | As a user I need the system to gracefully handle out-of-scope questions not covered by the uploaded document | Small | 3 | 3 |  | 8
US022 | As a user I need to select two or more documents for side-by-side comparison of key clauses and risk flags | Large | 2 | 3 |  | 40
US023 | As a user I need a comparison summary that highlights differences in obligations and risk levels across selected documents | Medium | 2 | 3 |  | 24
US024 | As a user I need to receive email or in-app notifications when document processing is complete or a high-risk clause is detected | Medium | 3 | 3 |  | 16
US025 | As an admin I need to view all registered users and their document upload activity on an admin dashboard | Medium | 2 | 3 |  | 16
US026 | As an admin I need to view platform-wide analytics (total documents, common doc types, average risk scores) | Medium | 3 | 3 |  | 16
US027 | As an admin I need to manage user roles (promote to Legal Professional, suspend accounts) | Small | 3 | 3 |  | 8
US028 | As an admin I need to view AI model performance metrics and flag incorrect outputs for retraining | Medium | 3 | 3 |  | 16
Note on D8: Unknown Author: stakeholdermap.com: Whatever method you are using for estimation. It could be story points, Fibonacci scale or T-shirt sizes - small, medium, large.
Note on E8: Unknown Author: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on F8: Unknown Author: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on G8: Unknown Author: stakeholdermap.com: An optional field for the person responsible for the completion of the User Story.
Note on H8: Unknown Author: stakeholdermap.com: This is an optional field for estimated effort in hours or days.

## PROJECT DETAILS
PROJECT NUMBER | PROJ-001
PROJECT NAME | Legal Document Clause Analyzer
PROJECT MANAGER | Ayush, Rishab
DATE | 2026-03-16
VERSION | 1.0

## DROPDOWN MENUS
PRIORITY | SPRINT
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6
7
8
9
10
TO EDIT THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Source to match the values you want to appear in the menu.
TO DELETE THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Allow to Any value.

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel